## Client planning checklist
#VALUE!
Client event planning checklist
EVENT | EVENT NAME
TENANCY START DATE | 2025-01-01
A letter of concern will be issued if the requested documents are not submitted within the timeline specified below.
ITEM | DATE COMPLETED BY | TIMELINE | COMPLETED
HEALTH & SAFETY DOCUMENTS
Event risk assessment including fire risk assessment | 2024-12-04 | 28 days
Contractor risk assessment (if required) | 2024-12-04 | 28 days
Exhibitor risk assessments for significant risks only | 2024-12-04 | 28 days
Construction Phase Plan | 2024-12-04 | 28 days
Onsite health and safety Nebosh rep and certs | 2024-12-04 | 28 days
Public liability insurance (Amount stated in license) | 2024-12-04 | 28 days
Structural Engineer (Campbell Reith) appointment | 2024-12-04 | 28 days
Boulevard permit to build and break | 2024-12-18 | 14 days
FLOORPLAN REQUIREMENTS
Floorplan with ducts (& services requirements) | 2024-12-04 | 28 days
Final plans | 2024-12-18 | 14 days
Mark out date | TBC
EVENT STRUCTURES
Registration plans (1:200) | 2024-12-04 | 28 days
Boulevard plan (1:200) (if required) | 2024-12-04 | 28 days
Feature plans (1:200) | 2024-12-04 | 28 days
COMPLEX STRUCTURES & PLANS
Seating plans (tiered / flat floor) (1:200) | 2024-12-04 | 28 days
Details to H&S and structural engineer for sign off | 2024-12-04 | 28 days
Complex structure space only plans and documents submitted | 2024-12-04 | 28 days
Complex structure permission to build letter received | 2024-12-04 | 28 days
EXCEL SERVICES
Piped orders | 2024-12-04 | 28 days
Rigging orders | 2024-12-04 | 28 days
ITC orders | 2024-12-04 | 28 days
Media orders | 2024-12-04 | 28 days
Excel London Hospitality (ELH) orders | 2024-12-04 | 28 days
Mains orders | 2024-12-18 | 14 days
Banner delivery | 2024-12-27 | 5 days
SECURITY
Event security plans | 2024-12-04 | 28 days
Security schedule | 2024-12-04 | 28 days
Security dot plans | 2024-12-04 | 28 days
CT risk assessment | 2024-12-04 | 28 days
Fire briefing times/numbers/positions | 2024-12-18 | 14 days
GENERAL INFORMATION REQUIRED
Event agenda build/break/open | 2024-12-04 | 28 days
Exhibitor list (GDPR compliant) | 60 days prior to tenancy
Exhibitor manual to check | 14 days prior to tenancy
Webshop approval | 14 days prior to tenancy
Furniture initial requirements | 2024-12-04 | 28 days
Voyage Control Form Completed | 2024-12-04 | 28 days
Voyage Control System Checked / Published | 2024-12-11 | 21 days
Contact list for onsite client/contractor | 2024-12-18 | 14 days
Set Precon meeting & daily meetings with client during tenancy | 2024-12-18 | 14 days
Furniture final requirements | 2024-12-25 | 7 days
POST-EVENT
Close event - Client to receive final billing details | 14 days post event
Debrief meeting with client | As soon as convenient post-event
Note on B7: Excel London: Enter the date (e.g 20 Feb 25) for the first day of tenancy then the "DATE COMPLETED BY" will update itself.